## Checklist-ja
No | カテゴリ | チェック項目 | Status | Notes
1 | 方針 | なぜ移行するのかを 1 文で言える
2 | 方針 | 今回の着地点が **Windows 専用の modern .NET** なのか、**将来のクロスプラットフォーム化** なのか決まっている
3 | 方針 | target の .NET バージョンを決めた
4 | 方針 | 今回のスコープに **含めないもの**（EF Core 化、認証刷新、クラウド全面移行など）が決まっている
5 | 現行 .NET Framework 側の整備 | .NET Framework 4.7.2 以降、できれば 4.8.1 に寄せた
6 | 現行 .NET Framework 側の整備 | 依存関係を最新寄りへ上げた
7 | 現行 .NET Framework 側の整備 | `packages.config` の有無を洗った
8 | 現行 .NET Framework 側の整備 | `PackageReference` 化の可否を確認した
9 | 現行 .NET Framework 側の整備 | SDK スタイル化の可否を確認した
10 | 現行 .NET Framework 側の整備 | 現行アプリがその状態でビルド・起動・テストできる
11 | アプリ種別と技術選定 | クラスライブラリ / デスクトップ / Web / WCF などの種別ごとに難易度を分けた
12 | アプリ種別と技術選定 | WinForms / WPF が Windows 専用のままだと理解している
13 | アプリ種別と技術選定 | ASP.NET Framework は ASP.NET Core への app model 移行だと理解している
14 | アプリ種別と技術選定 | Web Forms の UI 層置換を見積もりに入れた
15 | アプリ種別と技術選定 | WCF はクライアントとサーバーを分けて評価した
16 | 非対応技術・要注意 API | `AppDomain` 依存を洗った
17 | 非対応技術・要注意 API | Remoting / `MarshalByRefObject` / `BeginInvoke` / `EndInvoke` を洗った
18 | 非対応技術・要注意 API | CAS / Security Transparency / COM+ / WF を洗った
19 | 非対応技術・要注意 API | BinaryFormatter 依存を洗った
20 | 非対応技術・要注意 API | `System.Web` 依存を洗った
21 | Windows 専用依存 | レジストリ、WMI、EventLog、Windows Service、Directory Services の利用を洗った
22 | Windows 専用依存 | `System.Drawing.Common` の利用を洗った
23 | Windows 専用依存 | COM / ActiveX / Office Interop / P/Invoke / ネイティブ DLL を洗った
24 | Windows 専用依存 | x86 / x64 / ARM64 の制約を確認した
25 | shared library とデータアクセス | shared library を **業務ロジック / app model 密着層** に分類した
26 | shared library とデータアクセス | `netstandard2.0` 化できるものを洗った
27 | shared library とデータアクセス | multi-target が必要なライブラリを洗った
28 | shared library とデータアクセス | EF6 を残して runtime だけ先に移せるか判断した
29 | shared library とデータアクセス | EDMX / Designer 依存を確認した
30 | 運用と build | 設定ファイルの棚卸しをした
31 | 運用と build | 配布方式（IIS / Service / MSI / ClickOnce など）を確認した
32 | 運用と build | ログ / 監視 / 権限 / 実行アカウント前提を確認した
33 | 運用と build | CI/CD と build agent の更新が必要か確認した
34 | 運用と build | ロールバック手順を作った

## Checklist-en
No | Category | Checklist Item | Status | Notes
1 | Direction | We can explain in one sentence why we are migrating
2 | Direction | We have decided whether the landing zone is **Windows-only modern .NET** or **future cross-platform**
3 | Direction | We have chosen the target .NET version
4 | Direction | We have explicitly listed what is **out of scope** for this phase, such as EF Core migration, auth redesign, or full cloud relocation
5 | Current .NET Framework cleanup | We moved the Framework side to 4.7.2 or later, ideally 4.8.1
6 | Current .NET Framework cleanup | We updated dependencies toward current supported versions
7 | Current .NET Framework cleanup | We checked where `packages.config` still exists
8 | Current .NET Framework cleanup | We evaluated `PackageReference` conversion feasibility
9 | Current .NET Framework cleanup | We evaluated SDK-style conversion feasibility
10 | Current .NET Framework cleanup | The current application still builds, starts, and passes tests in that cleaned-up state
11 | Application model and technology choices | We estimated difficulty separately by class library, desktop, web, WCF, and similar project types
12 | Application model and technology choices | We understand that WinForms and WPF remain Windows-only
13 | Application model and technology choices | We understand that ASP.NET Framework to ASP.NET Core is an app-model migration
14 | Application model and technology choices | We included Web Forms UI replacement in the estimate
15 | Application model and technology choices | We evaluated WCF clients separately from WCF servers
16 | Unsupported or high-risk technology | We audited AppDomain dependency
17 | Unsupported or high-risk technology | We audited Remoting, `MarshalByRefObject`, `BeginInvoke`, and `EndInvoke`
18 | Unsupported or high-risk technology | We audited CAS, Security Transparency, COM+, and Workflow Foundation
19 | Unsupported or high-risk technology | We audited BinaryFormatter dependency
20 | Unsupported or high-risk technology | We audited `System.Web` dependency
21 | Windows-only dependency | We audited registry, WMI, Event Log, Windows Service, and Directory Services usage
22 | Windows-only dependency | We audited `System.Drawing.Common` usage
23 | Windows-only dependency | We audited COM, ActiveX, Office Interop, P/Invoke, and native DLL usage
24 | Windows-only dependency | We checked `x86`, `x64`, and `ARM64` restrictions
25 | Shared libraries and data access | We classified shared libraries into business logic versus app-model-dependent layers
26 | Shared libraries and data access | We identified libraries that can move to `netstandard2.0`
27 | Shared libraries and data access | We identified libraries that need multi-targeting
28 | Shared libraries and data access | We decided whether EF6 can remain while only the runtime moves first
29 | Shared libraries and data access | We checked EDMX and designer dependency
30 | Operations and build | We inventoried configuration files
31 | Operations and build | We reviewed deployment shape such as IIS, Service, MSI, and ClickOnce
32 | Operations and build | We reviewed logging, monitoring, privilege, and execution-account assumptions
33 | Operations and build | We reviewed whether CI/CD and build agents need updates
34 | Operations and build | We prepared rollback procedures